## Contract Overview
Vendor Contract Portfolio Summary — Q3 2026
Northbridge Health Network ¦ Prepared by: Karen Liu (VMO) ¦ Date: 11-JUL-2026
VND ID | Vendor | Category | Contract Type | Value | SLA Status | SLA Response | SLA Uptime | Service Credit Clause | Renewal Date | Renewal Type
VND-001 | Lumina Health Systems | EHR & Clinical Software | Implementation & Support MSA | $1,200,000 | Green | 4h P1, 8h P2 | 99.5% | MSA clause 7.4 — 8% of impl. fee per week of delay | 01-MAR-2027 | Fixed term — 120-day notice
VND-002 | MediTech Biomedical Inc. | Medical & Biomedical Equipment | PM & Calibration MSA | $340,000 | Green | 48h preventive, 4h critical | N/A | 10% of monthly fee per month with SLA breach | 01-SEP-2026 | Auto-renewal — 60-day notice
VND-003 | PharmaLink Distributors | Clinical Supplies & Pharmacy | Distribution Agreement | $520,000 | Amber | 5 biz days standard, 24h urgent | N/A | Clause 5.2 — 5% line-item value per week of delay | 15-OCT-2026 | Annual — 90-day rebid notice
VND-004 | ClearPoint Clinical Solutions | Clinical Software (CPOE & Lab) | License & Support Agreement | $280,000 | Green | 2h P1, 8h P2 | 99.5% | 5% monthly license per month below 99.5% uptime | 01-MAR-2027 | Fixed term — 120-day notice

## Performance KPIs
Performance KPIs by Vendor
VND ID | Vendor | KPI 1 | Target 1 | KPI 2 | Target 2 | KPI 3 | Target 3
VND-001 | Lumina Health Systems | Go-live on schedule | Met ✓ | Post-go-live incidents | < 5/month | Training completion | ≥ 95%
VND-002 | MediTech Biomedical Inc. | Calibration completion rate | ≥ 98% | Certificate turnaround | ≤ 48h | Missed JC equipment items | Zero
VND-003 | PharmaLink Distributors | On-time delivery rate | ≥ 95% | Formulary-kit fill rate | ≥ 99% | Controlled-substance compliance | 100%
VND-004 | ClearPoint Clinical Solutions | System uptime | ≥ 99.5% | P1 incident response | ≤ 2h | Upgrade deployment | On schedule

## Commitments & Milestones
Open Commitments & Upcoming Milestones
VND ID | Vendor | Open | Next Milestone | Due Date | Owner | Status
VND-001 | Lumina Health Systems | 0 | Post-go-live support period ends | 22-JUL-2026 | Karen Liu | On Track
VND-002 | MediTech Biomedical Inc. | 2 | Patient-monitor calibration (12 units) | 14-JUL-2026 | Karen Liu | On Track
VND-002 | MediTech Biomedical Inc. |  | Autoclave validation | 18-JUL-2026 | Karen Liu | On Track
VND-003 | PharmaLink Distributors | 1 | Controlled-substance audit log binders | 16-JUL-2026 | Karen Liu | Delayed (was 11-JUL)
VND-004 | ClearPoint Clinical Solutions | 2 | CPOE v4.2 staging deployment | 17-JUL-2026 | Karen Liu | On Track
VND-004 | ClearPoint Clinical Solutions |  | CPOE v4.2 production cutover | 21-JUL-2026 | Karen Liu | On Track

## JC Compliance
Joint Commission Vendor Compliance Status
VND ID | Vendor | Requirement 1 | Requirement 2 | JC Readiness
VND-001 | Lumina Health Systems | Medication-management data integrity | HIPAA BAA | Ready ✓
VND-002 | MediTech Biomedical Inc. | Environment-of-care equipment standards | FDA biomedical device calibration | Pending (certs by 20-JUL)
VND-003 | PharmaLink Distributors | DEA controlled-substance record-keeping | Medication-management supply chain | At Risk (binder delivery 16-JUL)
VND-004 | ClearPoint Clinical Solutions | Medication-management alerting (Appendix C) | HL7 interop with LuminaEHR | On Track (cutover 21-JUL)

## Renewal Calendar
Contract Renewal Calendar
VND ID | Vendor | Renewal Date | Notice Period | Notice Window Opens | Procurement Recommendation
VND-002 | MediTech Biomedical Inc. | 01-SEP-2026 | 60 days | 03-JUL-2026 | Renew with tighter 24h SLA (currently 48h)
VND-003 | PharmaLink Distributors | 15-OCT-2026 | 90 days | 17-JUL-2026 | Rebid controlled-substance segment; keep formulary-kit line
VND-004 | ClearPoint Clinical Solutions | 01-MAR-2027 | 120 days | 01-NOV-2026 | Flag v4.2 performance for renewal negotiation
VND-001 | Lumina Health Systems | 01-MAR-2027 | 120 days | 01-NOV-2026 | No action now